- True/False

- Needs resolution is the initial phase of the project life cycle. 

ANSWER: F

- Before a request for proposal is prepared, the customer must clearly define the problem or need. 

ANSWER: T

- The purpose of preparing a request for proposal is to state, comprehensively and in detail, what is required, from the contractor’s point of view, to address the identified need. 

ANSWER: F

- In many situations a formal RFP may not be prepared. 

ANSWER: T

- Instead of a formal RFP sometimes needs are communicated orally instead of in writing.  

ANSWER: T

- A statement of work (SOW) is an optional part of an RFP.  

ANSWER: F

- An RFP includes the customer regulations, which define specifications and attributes. 

ANSWER: F

- Deliverables are the tangible items that the contractor is to supply. 

ANSWER: T

- Any customer-supplied items are not listed in an RFP.  

ANSWER: F

- In a cost contract the customer will pay the contractor a fixed amount regardless of how much the work actually costs the contractor. 

ANSWER: F

- Progress payments, based on a percentage of the total price, are those made as certain milestones are accomplished.  

ANSWER: T

- An RFP should vaguely state the schedule for completion of the project.  

ANSWER: F

- Instructions in an RFP might state the maximum number of pages, the number of details the customer wants the contractor to show regarding the costs, and other specifications. 

ANSWER: T

- The RFP should indicate the due date by which the customer expects potential contractors to submit proposals. 

ANSWER: T

- In all cases an RFP should indicate the funds the customer has available to spend on the project 

ANSWER: F

- Business customers and contractors consider the RFP/proposal process to be a competitive situation. 

ANSWER: T

- All project life cycles include the preparation of a written request for proposal and subsequent proposals from contractors. 

ANSWER: F

18.	Project selection involves evaluating various needs or opportunities, and then deciding which of these should be moved forward as a project.

- ANSWER: T

19.	During project selection only quantitative factors should be evaluated.

ANSWER: F

- The purpose of preparing a request for proposal is to state, comprehensively and in detail, what is required, from the customer’s point of view, to address the identified need.

- ANSWER: T

- The purpose of preparing a request for proposal is to state, comprehensively and in detail, what is required, from the developer’s point of view, to address the identified need.

- ANSWER: F

- An RFP must provide a statement of work (SOW)

ANSWER: T

- Before a request for proposal is prepared, the customer must clearly define the problem or need. This may mean gathering data about the magnitude of the problem.

ANSWER: T

- Multiple Choice

- __________________ is the initial phase of the project life cycle.

  - Needs resolution

  - Needs identification

  - Problem generation

  - Brainstorming

- ANSWER: B

- Before a ______________ is prepared, the customer must clearly define the problem or need.

  - Request for solutions

  - Request for procedures

  - Request for processing

  - Request for proposal

- ANSWER: D

- The purpose of preparing a request for proposal is to state, comprehensively and in detail, what is required, from the customer’s point of view, to address the ___________.

  - cost issues

  - identified need

  - technical ideas

  - work breakdown goals

- ANSWER: B

- A ________________ deals with the scope of the project, outlining the tasks or work elements the customer wants the contractor or project team to perform.

  - statement of objectives

  - statement of goals

  - statement of work

  - statement of constraints

- ANSWER: C

- The RFP must include the customer requirements, which define ____________ and attributes.

  - specifications

  - documents

  - spatial relations

  - activities

- ANSWER: A

- ________________ are the tangible items that the contractor is to supply.

  - deliverables

  - documents

  - SOW’s

  - work breakdowns

- ANSWER: A

- In a _____________ contract, the customer will pay the contractor a set amount regardless of how much the work actually costs the contractor.

  - flat price

  - time-based

  - fixed price

  - time and materials

- ANSWER: C

- ______________, based on a percentage of the total price, are those made as certain milestones are accomplished.

  - pattern payments

  - direct fees

  - progress statements

  - progress payments

- ANSWER: D

- The __________ criteria are the criteria that the customer will use to evaluate proposals from competing contractors in order to select the one to perform the project.

  - evaluation

  - evolving

  - schedule

  - cost

- ANSWER: A

- Business or government customers may hold a _______ meeting to explain the RFP and answer questions from interested contractors.

  - bribers

  - bidders

  - post-implementation

  - work scope

- ANSWER: B

- The first step in the project selection process is to:

  - estimate the sales from the system or product

  - list assumptions for the opportunity

  - study legal barriers

  - develop a set of criteria to evaluate each opportunity

ANSWER: D

- Evaluating various needs or opportunities, and then deciding which should be moved forward as a project is called:

  - Project Decision-Making

  - Project Selection

  - Project Projections

  - Project Sorting and Classification

ANSWER: B